## Format
MES's Institute of Management and Career Courses (IMCC)
Mini Project FY MCA- SEM I
Academic Year 2020-21
Name of Project: |  | Fun Learn
Project Start |  | 2021-02-18 | Module alloted
Other Members
Team Member-1 |  | Raj Bhattad | Stack: Array Implementation
Team Member-2 |  | Utkarsh Bhangale | Stack: Array Implementation
Team Member-3 |  | Anuj Gaikwad | Queue: Array Implementation
Team Member-4 |  | Suraj Biyani | Queue: Array Implementation
Level | WBS | Task Description | Learnings | Start Date | End Date | Remark | Approved By & Date
1 | 1 | Project Topic decision
2 | 1.1 | Meeting with team members | Had a meeting with team members about different project ideas | 2021-02-25 | 2021-02-26
2 | 1.2 | Topic discussion | Discussed about the short listed project ideas. | 2021-02-26 | 2021-02-27
3 | 1.2.1 | Topic finalisation | Finalized the project idea and name of the project | 2021-02-28 | 2021-03-01
3 | 1.3 | Scope coverage | Decided the scope of the project | 2021-03-19 | 2021-03-20
4 | 1.3.1 | Scope approval | Got an approval from our project mentor for scope | 2021-04-07 | 2021-04-09
1 | 2 | Synopsis Submission
2 | 2.1 | Scope |  | 2021-04-01 | 2021-04-09
3 | 2.2 | Modules |  | 2021-04-02 | 2021-04-09
3 | 2.3 | Technology Description | Described the technologies to be used in the project.
1 | 3 | Submission – algorithm | Submitted the algorithm of the website.
2 | 3.1 | Discussion | Decided the flow algorithm of the website | 2021-04-07 | 2021-04-23
3 | 3.2 | Representation | Presented the algorithm to the project mentor | 2021-04-09 | 2021-04-23
1 | 4 | Database design/ Input design
2 | 4.1 | Discussion on Data Fields required | Discussion held to decide the data fields required. | 2021-04-23 | 2021-04-23
3 | 4.2 | Preparing List of fields | Prepared a list of data fields required in the database. | 2021-04-23 | 2021-04-23
4 | 4.3 | Table design | Designed the table for the data dictionary. | 2021-04-23 | 2021-04-23
1 | 5 | Screen design
2 | 5.1 | Assigning screens to mambers | Assigned screen designs to members | 2021-04-11 | 2021-04-12
3 | 5.2 | Designing screen | Members of group designed screen according to their module | 2021-04-12 | 2021-04-13
1 | 6 | Validation
2 | 6.1 | Applying contraints on fields | Constraints were applied to specific fields | 2021-04-23 | 2021-04-25
3 | 6.2 | code against field validation | Done coding for validations | 2021-04-23 | 2021-04-25
1 | 7 | Integration of screens/ modules
2 | 7.1 | Designing Menu Screen | Menu screen was designed | 2021-04-26 | 2021-04-26
3 | 7.2 | Call every screen from Menu | Done coding to call every screen from menu | 2021-04-26 | 2021-04-26
1 | 8 | Project Execution
2 | 8.1 | Debuging for error | Found the errors in the project | 2021-04-28 | 2021-05-01
3 | 8.2 | Resolve errors | Resolved the errors in the project | 2021-05-02 | 2021-04-07
* WBS = Work Breakdown Structure